{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["长安区√"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"长安区√","index":0,"n_rows":144,"n_cols":25,"rows_kept":144,"merged":[[0,0,0,24],[1,23,1,24],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,4,3],[2,4,4,4],[2,5,4,5],[2,6,3,7],[2,8,4,8],[2,9,4,9],[2,10,4,10],[2,11,3,12],[2,13,3,14],[2,15,2,21],[2,22,4,22],[2,23,4,23],[2,24,4,24],[3,15,4,15],[3,16,3,20],[3,21,4,21]],"flags":["formulas_cached_only"]}
["长安区财政衔接资金（巩固拓展脱贫攻坚成果和乡村振兴任务）项目计划备案明细表"]
[{"$nulls":23},"单位：万元"]
["项目类型","项目名称","项目内容及建设规模","建设期限             （起止时间）","绩效目标","项目个数","项目实施  地点",null,"脱贫村（是/否）","重点帮扶镇（是/否）","重点帮扶村（是/否）","直接受益脱贫人口（含监测对象）",null,"受益总人口",null,"资金投入（万元）",{"$nulls":6},"项目\n实施\n单位","行业主管部门","财政资金 支持环节"]
[{"$nulls":15},"合计","财政衔接资金",{"$nulls":4},"其它资金投入"]
[{"$nulls":6},"镇","村",{"$nulls":3},"户数","人数","户数","人数",null,"小计","中央","省级","市级","县级"]
["总 计",{"$nulls":4},98,{"$nulls":9},15961.29,13454.45,0,0,7448.75,5460,880,0,0,0]
["一、产业发展",{"$nulls":4},17,{"$nulls":9},5288,4408,0,0,4275,10,880,0,0,0]
["1.生产项目",{"$nulls":4},13,{"$nulls":9},5075,4195,0,0,4195,0,880]
["①种植业基地(种植业)",{"$nulls":4},12,{"$nulls":9},5025,4145,0,0,4145,0,880]
[null,"2023年黄良街道古城村秦北蝴蝶兰温室建设项目","蝴蝶兰智能温室及配套设备提升，面积3168平方米。","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"黄良街道","古城村","否","否","否",38,80,620,1500,500,400,null,null,400,null,100,"区农业农村局","区农业农村局"]
[null,"王曲街道黄甫村大美林庄精品采摘园项目","新建精品采摘温室连栋大棚，土壤改良及引进新品种果蔬。","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"王曲街道","皇甫村","否","否","否",10,32,60,200,330,240,null,null,240,null,90,"区农业农村局","区农业农村局"]
[null,"长松翠竹现代农业生态观光园被型日光大棚建设项目","新建被型日光大棚8000平米。","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"子午街道","子午镇村","否","否","否",38,75,30,102,290,200,null,null,200,null,90,"区农业农村局","区农业农村局"]
[null,"太阳葡萄小镇智能温室建设项目","建设智能温室3000平米，搭建葡萄钢架避雨棚30亩，原有葡萄园水肥一体化改造150亩，葡萄品种改良50亩","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"引镇街道","南寨西村","否","否","否",28,52,477,1530,1000,400,null,null,400,null,600,"区农业农村局","区农业农村局"]
[null,"砲里街办南桑村水果西红柿大棚建设项目","增加新品种水果西红柿种植，项目建设温室大棚共7栋，（单栋100米长，12米宽）六栋7200平方米，一栋4000平方米，玻璃阳光大棚；大棚生产附属设施：水电，机械，降温等辅助设施。","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"砲里街道","南桑村","否","否","否",21,46,995,2450,400,400,null,null,400,null,null,"区农业农村局","区农业农村局"]
[null,"上堡子经济合作社“南山农场”有机蔬菜培育项目","建设40000平智能温室玻璃大棚，大棚外围可抵御沟内日常自然灾害风险，通过智慧农业系统实现智能化种植，达到降本增效的效果，引进专业化种植技术，带领村民共同发展致富。","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"杨庄街道","侯官寨村","否","否","否",17,36,387,1200,500,500,null,null,500,null,null,"区农业农村局","区农业农村局"]
[null,"祥峪口鲜切花种植项目","建设温室大棚及棚内加温和通风设施、水肥一体化全自动灌溉系统、无土栽培基质条栽培系统、道路、水源等基础设施","2023年11月1日-2024年4月1日","增加村级集体和脱贫户收入",null,"滦镇街道","祥峪村","否","否","否",18,32,1156,4082,400,400,null,null,400,null,null,"区乡村振兴公司","区乡村振兴公司"]
[null,"黄良鲜切花种植项目","建设温室大棚及棚内加温和通风设施、水\n肥一体化全自动灌溉系统、无土栽培基质条栽培系统、道路、水\n源等基础设施","2023年11月1日-2024年4月1日","增加村级集体和脱贫户收入",null,"黄良街道","北良村","否","否","否",11,26,636,2056,400,400,null,null,400,null,null,"区乡村振兴公司","区乡村振兴公司"]
[null,"“长安花”乡村振兴实体店项目","在长安区各大高校、医院及街办开设“长安花”乡村振兴实体店约 40 家，并同步制作“长安花”小程序，线上线下业务同步开展","2023年11月1日-2024年4月1日","增加村级集体和脱贫户收入",null,"长安辖区内",null,"否","否","否",null,100,null,null,400,400,null,null,400,null,null,"区乡村振兴公司","区乡村振兴公司"]
[null,"南寨东村农业产业园项目","新建温室大棚30亩，种植果树100亩，修建生产路500米，新建灌溉井2个以及其他配套设施，新建看护房200平米。","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"引镇街道","南寨东村","否","否","否",28,49,451,1552,290,290,null,null,290,null,null,"区农业农村局","区农业农村局"]
[null,"南寨西村现代种植基地项目","新建阳光大棚10个，修建生产道路500米，配套看护房、仓库等","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"引镇街道","南寨西村","否","否","否",28,52,477,1530,225,225,null,null,225,null,null,"区农业农村局","区农业农村局"]
["⑤休闲农业与乡村旅游",{"$nulls":4},1,{"$nulls":9},50,50,null,null,50]
[null,"南寨东村民宿产业发展项目","整合村内空闲宅基地、闲散零星地，发展民宿产业（50万元）","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"引镇街道","南寨东村","否","否","否",28,49,451,1552,50,50,null,null,50,null,null,"引镇街办","区农业农村局"]
["2.加工流通项目",{"$nulls":4},2,{"$nulls":9},80,80,0,0,80,0,0,0,0]
["④品牌打造和展销平台",{"$nulls":4},2,{"$nulls":9},80,80,null,null,80]
[null,"南寨东村电商平台建设项目","建立特色产品展示中心100平米（18万元）；购置电脑及相关设备（12万元）","2024年6月1日-2024年12月30日","增加村级集体和脱贫户收入",null,"引镇街道","南寨东村","否","否","否",28,49,451,1552,30,30,null,null,30,null,null,"引镇街办","区农业农村局"]
[null,"沙场村数字乡村及电商农副产品售卖市场","打造建设农副产品加工及售卖场所",{"$nulls":3},"太乙宫街道","沙场村","否","否","否",19,44,null,null,50,50,null,null,50,null,null,"太乙宫街办","区农业农村局"]
["3.配套设施项目",{"$nulls":4},1,{"$nulls":9},123,123]
["①小型农田水利设施及产业配套基础设建设",{"$nulls":4},1,{"$nulls":9},123,123]
[null,"韦兆西村农田灌溉工程","对1200亩农田灌溉渠进行修复","2024年6月1日-2024年12月30日",null,null,"王莽街道","韦兆西村","否","否","否",23,51,893,2985,123,123,{"$nulls":5},"区农业农村局","区农业农村局"]
["5.金融保险配套项目",{"$nulls":4},1,{"$nulls":9},10,10,0,0,0,10]
["①小额贷款贴息",{"$nulls":4},1,{"$nulls":9},10,10,{"$nulls":3},10]
[null,"2024年脱贫人口及监测对象小额贷款贴息项目",{"$nulls":13},10,10,{"$nulls":3},10,null,null,"区乡村振兴局","区乡村振兴局"]
["二、就业项目",{"$nulls":4},2,0,0,0,0,0,0,0,0,0,360,360,0,0,0,360,0,0]
["1.务工补助",{"$nulls":4},1,{"$nulls":9},10,10,{"$nulls":3},10,null,null,"区乡村振兴局","区乡村振兴局"]
["①交通费补助",{"$nulls":4},1,{"$nulls":9},10,10,{"$nulls":3},10,null,null,"区乡村振兴局","区乡村振兴局"]
[null,"脱贫劳动力（含监测对象跨省交通补助）",{"$nulls":13},10,10,{"$nulls":3},10,null,null,"区乡村振兴局","区乡村振兴局"]
["5.公益性岗位",{"$nulls":4},1,{"$nulls":9},350,350,{"$nulls":3},350]
["①公益性岗位",{"$nulls":4},1,{"$nulls":9},350,350,{"$nulls":3},350]
[null,"2024年乡村公益性岗位补助","发放2024年乡村公益性岗位补助资金",{"$nulls":12},350,350,{"$nulls":3},350]
["三、乡村建设行动",{"$nulls":4},76,{"$nulls":9},8213.29,6586.45,0,0,3173.75,2990]
["1.农村基础设施（含产业配套基础设施）",{"$nulls":4},52,{"$nulls":9},6722.59,5524.25,0,0,2315.25,2390]
["①村庄规划编制（含修编）",{"$nulls":4},3,{"$nulls":9},720,720,0,0,0,720]
[null,"长安区魏寨乡村聚落集中连片发展示范区规划","核心村庄规划及详细规划","2024年6月1日-2024年12月30日",{"$nulls":9},3701,13103,220,220,{"$nulls":3},220,null,"区乡村振兴局","区乡村振兴局"]
[null,"长安区王曲-杜曲乡村聚落集中连片发展示范区规划","核心村庄规划及详细规划","2024年6月1日-2024年12月30日",{"$nulls":9},9040,26455,260,260,{"$nulls":3},260,null,"区乡村振兴局","区乡村振兴局"]
[null,"编制8个示范村村庄实用性规划","实用性村庄规划编制","2023年11月1日-2024年4月1日",{"$nulls":11},240,240,{"$nulls":3},240,null,"区乡村振兴局","区乡村振兴局"]
["②农村道路建设（通村路、通户路、小型桥梁等）",{"$nulls":4},20,{"$nulls":9},2848.34,1650,0,0,1650,0,0]
[null,"甫店村病害路面修复项目","修复甫店村赛格园区门前病害路面，铺设沥青路面14080平方米。",null,"解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"子午街道","甫店村","否","否","否",19,37,748,2646,210,{"$nulls":6},"子午街办","区住建局"]
[null,"递午村村内道路硬化项目","硬化村内道路，约3120平方米",null,"解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"子午街道","递午村","否","否","否",20,50,660,2236,94,{"$nulls":6},"子午街办","区住建局"]
[null,"杜角镇村内道路硬化项目","硬化西村及南豆角村4条道路，面积约2000㎡；西村2条主干道铺沥青，面积约3200㎡。",null,"解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"子午街道","杜角镇村","否","否","否",20,32,790,3124,120,{"$nulls":6},"子午街办","区住建局"]
[null,"营沟村村内道路硬化及雨水渠配套设施项目","硬化村内道路面积5757.73平米，及配套排水渠。","2023年8月1日-2023年12月1日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"杨庄街道","营沟村","否","否","否",20,60,531,1745,193.96,{"$nulls":6},"杨庄街办","区住建局"]
[null,"井塬村村内道路硬化项目","硬化村内道路1012平米","2023年8月1日-2023年12月1日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"杨庄街道","井塬村","否","否","否",13,36,304,1091,32.38,{"$nulls":6},"杨庄街办","区住建局"]
[null,"赵家坡常村出村路硬化项目","硬化前门村至岔道口村长1000米，宽，5米，硬化面积5000㎡","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"引镇街道","赵家坡常村","否","否","否",20,44,616,2256,150,{"$nulls":6},"引镇街办","区住建局"]
[null,"马厂村主干道油返砂修复项目","主干道硬化21000平方米；修复排水系统","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"王曲街道","马厂村","否","否","否",51,138,1132,3840,315,{"$nulls":6},"王曲街办","区住建局"]
[null,"查新村村内道路硬化","硬化8条道路，约2985㎡","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"鸣犊街道","查新村","否","否","否",31,107,419,1406,83,{"$nulls":6},"鸣犊街办","区住建局"]
[null,"曙光村道路硬化和提升","硬化村内道路750㎡，每平方米造价300元，提升道路15000㎡，每平米造价225元。","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"王曲街道","曙光村","否","否","否",66,169,502,1380,360,360,null,null,360,null,null,"王曲街办","区住建局"]
[null,"太乙村交通安全防护措施安装项目","太乙村十四组坡陡弯急需安装交安护1700米，每米300元;太乙村沿线（八、九、十一、十二组）建设交安护栏3300米，每米300元)。","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,150,150,null,null,150,null,null,"太乙宫街办","区交通局"]
[null,"南寨西村西进村路修复提升项目","铺设沥青2500㎡，修建排水渠及加盖盖板1000米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"引镇街道","南寨西村","否","否","否",28,52,477,1530,80,80,null,null,80,null,null,"引镇街办","区交通局"]
[null,"南寨西村村内道路修复项目","对村内道路铺设沥青16399㎡","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"引镇街道","南寨西村","否","否","否",28,52,477,1530,100,100,null,null,100,null,null,"引镇街办","区住建局"]
[null,"团结村村内道路硬化项目","硬化村内道路5720平方米，长1144米，宽5米，281元/平方米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"五台街道","团结村","否","否","否",5,10,318,960,161,161,null,null,161,null,null,"五台街办","区住建局"]
[null,"团结村返砂村内道路修复项目","修复村内3条返砂道路，长度1123米，6225平方米，100元/平方米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"五台街道","团结村","否","否","否",5,10,318,960,63,63,null,null,63,null,null,"五台街办","区住建局"]
[null,"抱龙村村内道路硬化","硬化村内道路面积1280㎡，每平方米390元","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"五台街道","抱龙村","否","否","否",24,51,459,1200,50,50,null,null,50,null,null,"五台街办","区住建局"]
[null,"藏龙寨村病害路面修复项目","桥西通曙光路（返沙路）2200平方米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"王曲街道","藏龙寨村","否","否","否",32,61,1038,4575,70,70,null,null,70,null,null,"王曲街办","区住建局"]
[null,"藏龙寨村村内道路硬化项目","硬化村内道路8750平方米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"王曲街道","藏龙寨村","否","否","否",32,61,1038,4575,280,280,null,null,280,null,null,"王曲街办","区住建局"]
[null,"翁家寨村道路拓宽改造","对长400米，进村路拓宽2米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,30,30,null,null,30,null,null,"滦镇街办","区住建局"]
[null,"沙场村内道路硬化项目","村东生产道路硬化长160米宽3米（四、五、六组）；村东生产道路硬化（沟沿）长130米宽3米；村西道路硬化（四组）长150米宽3米；沙场至崔家河产业路长1260米，宽4米","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"太乙宫街道","沙场村","否","否","否",20,44,808,2402,216,216,null,null,216,null,null,"太乙宫街办","区住建局"]
[null,"杜角镇村内道路硬化项目","硬化西村及南杜角村道路，硬化面积面积约550㎡，；病害路面修复，铺设沥青路面3200㎡。","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"子午 街道","杜角镇村","否","否","否",20,44,790,3124,90,90,null,null,90,null,null,"子午街办","区住建局"]
["③产业路、资源路、旅游路建设",{"$nulls":4},1,{"$nulls":9},50,50,0,0,50]
[null,"翁家寨生产路硬化项目","硬化长500米，宽3米的生产路","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,50,50,null,null,50,null,null,"滦镇街办","区交通局"]
["④农村供水保障设施建设",{"$nulls":4},22,null,null,"否","否","否",{"$nulls":4},3065.25,3065.25,0,0,576.25,1670]
[null,"魏寨村农村供水保障项目","1.1万米人畜饮水管道铺设,机井1眼,水表639个。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"魏寨街道","魏寨村","否","否","否",28,75,639,2077,360,360,{"$nulls":3},360,null,"魏寨街办","区水务局"]
[null,"高家湾村农村供水保障项目","更换管网6000米，安装智能水表660户。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"王曲街道","高家湾村","否","否","否",13,24,528,2060,150,150,{"$nulls":3},150,null,"王曲街办","区水务局"]
[null,"东祥村（东联村）农村供水保障项目","管网改造1500米，配套设备1套，户表改造56户。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"滦镇街道","东祥村","否","否","否",23,57,1245,5366,45,45,{"$nulls":3},45,null,"滦镇街办","区水务局"]
[null,"常宁村农村供水保障项目","新打人畜饮水井1口,新建管理房1座,修建蓄水池1座,水泵、配套配电柜及控制柜等配套设施，更换管道3000米。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"王曲街道","常宁村","否","否","否",24,55,641,3462,150,150,{"$nulls":3},150,null,"王曲街办","区水务局"]
[null,"百塔寺村（天子峪）农村供水保障项目","清洗原蓄水池，新建40立方米、20立方米2个蓄水池，增加相应消毒设备，更换供水管道8000米。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"子午街道","百塔寺村","否","否","否",30,63,685,2184,160,160,{"$nulls":3},160,null,"子午街办","区水务局"]
[null,"石砭峪新村农村供水保障项目","新建150立方米蓄水池1座","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"五台街道","石砭峪村","否","否","否",null,null,475,1669,50,50,{"$nulls":3},50,null,"五台街办","区水务局"]
[null,"石佛寺村农村供水保障项目","更换供水官网7000米,更换智能水表430户。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"黄良街道","石佛寺村","否","否","否",null,null,425,1273,230,230,{"$nulls":3},230,null,"黄良街办","区水务局"]
[null,"清水头村农村供水保障项目","更换自来水管道7500米。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"王莽街道","清水头村","否","否","否",18,47,775,3326,200,200,{"$nulls":3},200,null,"王莽街办","区水务局"]
[null,"河滩村农村供水保障项目","更换供水管道9500米,安装智能水表480个。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"引镇街道","河滩村","否","否","否",22,39,474,1690,175,175,{"$nulls":3},175,null,"引镇街办","区水务局"]
[null,"西垇村农村供水保障项目","管网改造（包含井、房、水泵、水箱、控制设备、机电设备、消毒、管道、智能表改造）","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"砲里街道","西垇村","否","否","否",42,105,194,2017,150,150,{"$nulls":3},150,null,"砲里街办","区水务局"]
[null,"子午镇村农村供水保障项目","更换老旧供水管道6500米。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"子午 街道","子午镇村","否","否","否",37,75,1879,5926,150,150,{"$nulls":5},"子午街办","区水务局"]
[null,"井塬村农村供水保障项目","打深水井1口，更换村内水管道1800余米，新增储水罐1个","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"杨庄街道","井塬村","否","否","否",13,36,304,1091,46,46,{"$nulls":5},"杨庄街办","区水务局"]
[null,"赵家坡常村农村供水保障项目","维修井房3座，更换供水管道7000米，安装智能水表408户。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"引镇街道","赵家坡常村","否","否","否",20,44,616,2256,160,160,{"$nulls":5},"引镇街办","区水务局"]
[null,"谢家岭村农村供水保障项目","东岭、西岭水网改造150万，智能水表安装60万","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"砲里街道","谢家岭村","否","否","否",38,99,1078,3592,210,210,{"$nulls":5},"砲里街办","区水务局"]
[null,"红庙村农村供水保障项目","水泵房改造，安装净水设备一套；配水管网改造3371米，阀门井5座，水表更换490个","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"滦镇街道","红庙村","否","否","否",3,5,422,1482,163,163,{"$nulls":5},"滦镇街办","区水务局"]
[null,"马厂村农村供水保障项目","修建蓄水池及井房1座，配套配电柜及变频控制柜各一套，敷设管道3000米","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"王曲街道","马厂村","否","否","否",51,138,1132,3840,90,90,{"$nulls":5},"王曲街办","区水务局"]
[null,"太乙村农村供水保障项目","3个蓄水池维修6万元（3米x4米x1.8米.2万元，3米x3米x1.5米.1.8万元3x5x1.8.2.2万元）。供水管网维修1800米x50元/米.9万元","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,15,15,null,null,15,null,null,"太乙宫街办","区水务局"]
[null,"团结村农村供水保障项目","更换供水管网6700米，205元/米，安装智能水表291套，890元/套","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"五台街道","团结村","否","否","否",5,10,318,960,163,163,null,null,163,null,null,"五台街办","区水务局"]
[null,"藏龙寨村农村供水保障项目","安装智能水表","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"王曲街道","藏龙寨村","否","否","否",32,61,1038,4575,65,65,null,null,65,null,null,"王曲街办","区水务局"]
[null,"沙场村农村供水保障项目","长约450米供水管网修建","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"太乙宫街道","沙场村","否","否","否",20,44,808,2402,10,10,null,null,10,null,null,"太乙宫街办","区水务局"]
[null,"杜角镇村农村供水保障项目","西村更换供水管道1200米及相关配套，南豆角村更换供水管道3000米及相关配套。","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"子午街道","杜角镇村","否","否","否",20,44,790,3124,140,140,null,null,140,null,null,"子午街办","区水务局"]
[null,"南寨东村饮用水管网改造项目","更新水网管道6500米，安装智能水表415个","2024年6月1日-2024年12月30日","改善全村供水质量，提高群众满意度",null,"引镇街道","南寨东村","否","否","否",28,49,451,1552,183.25,183.25,null,null,183.25,null,null,"引镇街办","区水务局"]
["⑥数字乡村建设（信息通信基础设施建设、数字化、智能化建设等）",{"$nulls":4},6,{"$nulls":9},39,39,0,0,39,0,0]
[null,"曙光村数字乡村项目","数字乡村平台的建设4个模块，计划整体投资5万元。","2024年6月1日-2024年12月30日","提升村集体收入",null,"王曲街道","曙光村","否","否","否",66,169,502,1380,5,5,null,null,5,null,null,"王曲街办","区委网信办、区投资商务局"]
[null,"南寨西村数字乡村项目","数字乡村平台的建设","2024年6月1日-2024年12月30日","提升村集体收入",null,"引镇街道","南寨西村","否","否","否",28,52,477,1530,5,5,null,null,5,null,null,"引镇街办","区委网信办、区投资商务局"]
[null,"团结村数字乡村项目","配备硬、软件设施2万元，搭建监控网络1万元、便民服务及辅助产业发展等数字化平台1万元","2024年6月1日-2024年12月30日","提升村集体收入",null,"五台街道","团结村","否","否","否",5,10,318,960,4,4,null,null,4,null,null,"五台街办","区委网信办、区投资商务局"]
[null,"藏龙寨村数字乡村平台项目","搭建数字乡村平台","2024年6月1日-2024年12月30日","提升村集体收入",null,"王曲街道","藏龙寨村","否","否","否",32,61,1038,4575,5,5,null,null,5,null,null,"王曲街办","区委网信办、区投资商务局"]
[null,"翁家寨村数字乡村项目","数字乡村平台的建设",null,"增加村级集体和脱贫户收入",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,10,10,null,null,10,null,null,"滦镇街办","区委网信办、区投资商务局"]
[null,"杜角镇村数字乡村建设","搭建数字乡村平台及相关配套设备。","2024年6月1日-2024年12月30日","提升村集体收入",null,"子午街道","杜角镇村","否","否","否",20,44,790,3124,10,10,null,null,10,null,null,"子午街办","区委网信办、区投资商务局"]
["2.人居环境整治",{"$nulls":4},9,{"$nulls":9},1062.2,1062.2,0,0,430,600]
["①农村卫生厕所改造（户用、公共厕所）",{"$nulls":4},1,{"$nulls":9},32.2,32.2,0,0,0,0]
[null,"井塬村公厕建设项目","建设公厕一座，60平米","2024年6月1日-2024年12月30日","完善基础设施，进一步提升村内人居环境",null,"杨庄街道","井塬村","否","否","否",13,36,304,1091,32.2,32.2,{"$nulls":5},"杨庄街办","区住建局"]
["②农村污水治理",{"$nulls":4},3,{"$nulls":9},146,146,0,0,146,0]
[null,"太乙村排水渠维修及建设","太乙村沿线2400米，每米300元","2024年6月1日-2024年12月30日","提高群众满意度",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,72,72,null,null,72,null,null,"太乙宫街办","区水务局"]
[null,"太乙村污水排放管道建设","太乙村九组800米，每米400元","2024年6月1日-2024年12月30日","提高群众满意度",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,32,32,null,null,32,null,null,"太乙宫街办","区水务局"]
[null,"沙场村水渠维修及建设","全村约800米明渠加盖板；长150米宽0.6米排水渠（四组）的修建；河道拦水坝修建及排水渠改造","2024年6月1日-2024年12月30日","提高群众满意度",null,"太乙宫街道","沙场村","否","否","否",20,44,808,2402,42,42,null,null,42,null,null,"太乙宫街办","区水务局"]
["④村容村貌提升",{"$nulls":4},5,{"$nulls":9},884,884,0,0,284,600,0]
[null,"百塔寺村人居环境整治提升项目","将百塔寺周边农户外立面进行改造提升","2024年6月1日-2024年12月30日","完善基础设施，进一步提升村内人居环境",null,"子午街道","百塔寺村","否","否","否",30,63,685,2184,300,300,{"$nulls":3},300,null,"子午街办","区住建局"]
[null,"太乙村人居环境提升","修复提升环保车位1400㎡x200元/㎡=30万，沿线安装充电桩20根，每根2000元，共4万。合计34万","2024年6月1日-2024年12月30日","改善群众居住环境提高群众满意度",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,34,34,null,null,34,null,null,"太乙宫街办","区住建局"]
[null,"杜角镇村人居环境整治","全村环境卫生整治，包括绿化修剪及种植、垃圾清运、危房拆除、局部破损路面修复及下水维修。","2024年6月1日-2024年12月30日","完善基础设施，进一步提升村内人居环境",null,"子午街道","杜角镇村","否","否","否",20,44,790,3124,100,100,null,null,100,null,null,"子午街办","区住建局"]
[null,"南寨东村人居环境提升项目","村内1000米道路绿植增补（15万）；新增景观5（50万）；墙体提升粉刷40000㎡（85万）","2024年6月1日-2024年12月30日","完善基础设施，进一步提升村内人居环境",null,"引镇街道","南寨东村","否","否","否",28,49,451,1552,150,150,null,null,150,null,null,"引镇街办","区农业农村局"]
[null,"黄良新村人居环境整治提升项目","将黄良新村周边农户外立面进行改造提升",{"$nulls":3},"黄良街道","黄良新村","否","否","否",null,null,861,null,300,300,{"$nulls":3},300,null,"黄良街办","区住建局"]
["3.农村公共服务",{"$nulls":4},15,{"$nulls":9},428.5,{"$nulls":3},428.5]
["②村卫生室标准化建设",{"$nulls":4},1,{"$nulls":9},20,20,0,0,20]
[null,"翁家寨村标准化卫生室建设","建设标准化卫生室一处",null,"提升全村人口身体素质，方便群众在家门口看病",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,20,20,null,null,20,null,null,"滦镇街办","区医保局"]
["③农村养老设施建设（养老院、幸福院、日间照料中心等）",{"$nulls":4},2,{"$nulls":9},50,50,0,0,50]
[null,"翁家寨村幸福院提升","幸福院提升",null,"解决全村老年人生活质量",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,30,30,null,null,30,null,null,"滦镇街办","区民政局"]
[null,"杜角镇村农村幸福院建设","建设农村幸福院休息室、娱乐室、餐厅及户外活动广场及健身器材等相关配套设施。","2024年6月1日-2024年12月30日","提升全村人口身体素质， 老年人生活质量",null,"子午街道","杜角镇村","否","否","否",20,44,790,3124,20,20,null,null,20,null,null,"子午街办","区民政局"]
["④公共照明设施",{"$nulls":4},6,{"$nulls":9},163,163,0,0,163]
[null,"曙光村修缮照明路灯","新装路灯70盏，每盏路灯购买安装2500元，维修路灯50盏，每盏费用1500元。","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"王曲街道","曙光村","否","否","否",66,169,502,1380,25,25,null,null,25,null,null,"王曲街办","区住建局"]
[null,"太乙村路灯安装及维修工程","更换老旧路灯，新增路灯。维修\n老旧路灯40盏x700元/盏=2.8万元\n更换新增90盏x3000元/盏=27万元","2024年6月1日-2024年12月30日","改善群众居住环境提高群众满意度",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,30,30,null,null,30,null,null,"太乙宫街办","区住建局"]
[null,"南寨西村西进村路路灯安装工程","安装LED路灯20个","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"引镇街道","南寨西村","否","否","否",28,52,477,1530,5,5,null,null,5,null,null,"引镇街办","区住建局"]
[null,"团结村太阳能路灯修复项目","修复村内80盏太阳能路灯，2500元/个","2024年6月1日-2024年12月30日","解决群众出行不便，完善基础设施，进一步提升村内人居环境",null,"五台街道","团结村","否","否","否",5,10,318,960,20,20,null,null,20,null,null,"五台街办","区住建局"]
[null,"百塔寺村太阳能路灯更换和新增项目","更换损坏太阳能路灯25个，每个1800元；新增太阳能路灯35个，每个3000元","2024年6月1日-2024年12月30日","完善基础设施，进一步提升村内人居环境",null,"子午街道","白塔寺村","否","否","否",30,63,685,2184,15,15,null,null,15,null,null,"子午街办","区住建局"]
[null,"沙场村主干路路灯安装及维护项目","蛟峪主干道40个，四组入户路7个及村内损坏路灯维修若干个","2024年6月1日-2024年12月30日","改善群众居住环境提高群众满意度",null,"太乙宫街道","沙场村","否","否","否",20,44,808,2402,68,68,null,null,68,null,null,"太乙宫街办","区住建局"]
["⑥其他（便民综合服务设施、文化活动广场、体育设施、村级客运站、农村公益性殡葬设施建设等",{"$nulls":4},6,{"$nulls":9},195.5,195.5,0,0,195.5]
[null,"太乙村村内监控安装","为村内主要干道、十字路口、地质灾害点、山洪危险区安装监控，共计170个","2024年6月1日-2024年12月30日","改善群众居住环境提高群众满意度",null,"太乙宫街道","太乙村","否","否","否",36,99,716,2236,20,20,null,null,20,null,null,"太乙宫街办","区住建局"]
[null,"百塔寺村法治宣传阵地","配备法治文化宣传栏5块，每块8000元，购置法律图书设置图书角10000元","2024年6月1日-2024年12月30日","提升全村治安环境",null,"子午街道","百塔寺村","否","否","否",30,63,685,2184,5,5,null,null,5,null,null,"子午街办","区司法局"]
[null,"翁家寨村法治宣传阵地","配备法治文化宣传栏，购置法律图书设置图书角",null,"提升全村治安环境",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,10,10,null,null,10,null,null,"滦镇街办","区司法局"]
[null,"杜角镇村法治宣传阵地","配备法治文化宣传栏，购置法律图书设置图书角。","2024年6月1日-2024年12月30日","提升全村治安环境",null,"子午街道","杜角镇村","否","否","否",20,44,790,3124,10,10,null,null,10,null,null,"子午街办","区司法局"]
[null,"南寨东村安保亮化项目","安装路灯181盏（90.5万元）；安装38个摄像头及主机一套（30万元）","2024年6月1日-2024年12月30日","完善基础设施，进一步提升村内人居环境",null,"引镇街道","南寨东村","否","否","否",28,49,451,1552,120.5,120.5,null,null,120.5,null,null,"引镇街办","区住建局"]
[null,"翁家寨村内监控安装","为村内主要干道、十字路口、安装监控，共计160个",null,"提升全村治安环境",null,"滦镇街道","翁家寨村","否","否","否",7,17,356,1537,30,30,null,null,30,null,null,"滦镇街办","区住建局"]
["四、异地搬迁后扶"]
["五、巩固三保障成果",{"$nulls":4},1,{"$nulls":9},100,100,0,0,0,100]
["2.教育",{"$nulls":4},1,{"$nulls":9},100,100,0,0,0,100]
["①享受“雨露计划”职业教育补助",{"$nulls":4},1,{"$nulls":9},100,100,0,0,0,100]
[null,"2024年“雨露计划”补助",{"$nulls":13},100,100,{"$nulls":3},100,null,null,"区乡村振兴局","区乡村振兴局"]
["六、乡村治理和精神文明建设",{"$nulls":4},"大类数量合计"]
["七、项目管理费",{"$nulls":4},1,{"$nulls":9},700,700,0,0,0,700]
["项目管理费",{"$nulls":14},700,700,0,0,0,700]
["项目管理费",{"$nulls":4},1,{"$nulls":9},700,700,0,0,0,700]
[null,"2023年衔接资金项目管理费",{"$nulls":13},700,700,{"$nulls":3},700,null,"区乡村振兴局","区乡村振兴局"]
["八、其他",{"$nulls":4},1,{"$nulls":9},1300,1300,0,0,0,1300,0]
["其他",{"$nulls":4},1,{"$nulls":9},1300,1300,0,0,0,1300,0]
[null,"2023年衔接资金项目续建项目",{"$nulls":13},1300,1300,{"$nulls":3},1300,null,"区乡村振兴局","区乡村振兴局"]